## Marketing Project Status
Area / Project type | Activity Name / overview | Business Priority | Activity detail - what is it? High level | Status | Activity Deadlines | RISK | Owner (in the marketing team) | What is the status? What is being worked on, what is Next action required from whom? Or by Whom? What decision was made e.g. on HOLD until xyz | Next Milestone | Document links - e.g. master doc for review, project plan
CRM | CRM cleanup - C-suite tagging | 21 - Highest Priority | Add C-Suite field & tag to CRM for emails |  | 2022-11-23 | On Track |  | xyz to review list of prospect with no job title
CRM | CRM cleanup - Remove duplicates | 21 - Highest Priority | Remove & merge duplicates - for xmas card send | In progress | 2022-11-23 | On Track |  | xyz to review list of "TBC delete?"
Measurement | November Analytic Report for Board | 8 - High | Monthly Stats for board |  | 2022-11-15 | Overdue
Measurement | December Analytic Report for Board | 8 - High | Monthly Stats for board |  | 2022-12-15
Content | Nov-22 Newsletter - Customer | 13 - v. High | Customer newsletter - product update re xyz |  | 2022-11-28 | Behind plan | Mkt - person A | Not got copy or feature detail from xyz
Content | Nov-22 Newsletter - Prospect | 21 - Highest Priority | Prospect newsletter - new product/solution, award win |  | 2022-11-28
Content | Dec-22 Newsletter - Customer/xmas card | 8 - High |  |  | 2022-12-16 |  |  | Need to agree content by xxxx & agree customer list | 2022-12-01
Content | Dec-22 Newsletter - Prospect/xmas card | 8 - High |  |  | 2022-12-16 |  |  | Need to agree content by | 2022-12-01
Content | Case Study - Client ABC | 21 - Highest Priority | Client ABC - Increase in sales xyz | In progress | 2022-12-05 | On Track |  | Copy approved by Client xyz , in design this week. | 2022-12-01
Content | Webinar - ABC | 13 - v. High | Webinar for xyz, Abc guest, purpose abc | To Start | 2022-12-06 | Behind plan |  | Need to sit down with xyz & agree abc | 2022-12-02
Content | Case Study - Client ABC | 21 - Highest Priority | Client ABC - Increase in sales xyz | In progress | 2022-12-07 | On Track |  |  | 2022-12-03
Content | Case Study - Client ABC | 13 - v. High | Client ABC - Increase in sales xyz | In progress | 2022-12-08 | On Track |  |  | 2022-12-04
Sales Collateral | Pitch Deck 1 - Redesign | 21 - Highest Priority |  |  |  | Behind plan |  | Waiting for review from xyz
Sales Collateral | Email template abc for sales team A | 13 - v. High | Email template abc for sales team A | On Hold | 2022-11-25 | Overdue |  | Re-start after pitch deck is finished
Hubspot Leadscoring | Hubspot Leadscoring Implementation | 13 - v. High | Setup leadscoring - for sales MQL | To Start | 2022-12-01 | Behind plan |  | Need to write agency brief for pitch this week, if can put xyz on hold
SEO | Paid media set up
SEO | SEO “quick wins” - meta descriptions | 8 - High
SEO | Google analytics implementation & tracking | 21 - Highest Priority
Website | Website Redesign brief
Website | Website key page copy refinement
Social - LinkedIn | Linkedin Campaign ABC

## Drop downs
v select status
To Start
In progress
Review/Amends
with x for Approval
In Testing
Live / Done
On Hold
21 - Highest Priority
13 - v. High
8 - High
5 - Medium
3 - Low priority
1 - Lowest priority
Overdue
Behind plan
On Track
Marketing person A
Marketing person B
Marketing person C
Marketing person D